## Sheet1
| Survey Software: Individual Diagnostic | slide
1 | Hope the “Resources – Core Creators” will change once the site link is live. This has been given as feedback before as well. What will it say? Words like “valueinsights” will be fine. | 1 | done
2 | State should not be visible as a field for International locations as not every country will have a state – this feedback was given in review 9 but has not been fixed. For India, it should show Country¦State (drop-down)¦City¦ Postal Code for International locations, it should show Country¦City¦Postal Code. | 2 | done
3 | •Country for the invoice is registered as Iceland, the invoice is coming in USD (see next slide) but the amount should be blank since we have not finalized the fees for international locations – the fees are not USD 1000. |  | done
4 | •From which Country Field is the data being picked up in the final invoice – the one highlighted in red or blue? It should be the one highlighted in red |  | done
5 | The USD figures are not yet finalized, so this should show zero, unless this has been put as dummy data. | 3 | done
6 | Please check if the amount field has been linked to the INR fees and if so it needs to change to where the data will be stored in the system for USD fees. |  | done
7 | For India, the State should be visible in the address here before Country | 4 | done
8 | Remove the word “tax” – it should say Recipient GST No. |  | done
9 | It should say No. of Licenses Purchased – as has been provided in the sample template | 5 | done
| •The GST calculation format for states other than Maharashtra is correct. But where the State is Maharashtra, as provided in the Invoice template it should show data for CGST and SGST and not IGST. (see the invoice format provided). |  | done
•CGST (9%)
•SGST (9%)
•As provided in the Sample invoice format, mention all the taxes in the template
•CGST (9%)
•SGST (9%)
•IGST (18%)
•When the buyer mentions the state as Maharashtra, the tax amounts should be shown for CGST and SGST and IGST should be blank
•Where the buyer mentions any state other that Maharashtra or any international country, the tax amount should be shown for IGST and CGST and SGST should remain blank
10 | •The address in the invoice should come from the place highlighted by red border | 6 | done
•Postal code should not be included in the address in the invoice – so all the fields highlighted in red above excluding the postal code should be populated in the invoice
11 | •The address, city, country, postal code data that has been provided by the user at the time of registration should be automatically populated in this box. |  | done
| •Only the missing fields should be editable e.g. address, city, state (for India) postal code which the user may not have provided at time of registration since they are non mandatory at the time of registering for the Individual diagnostic. |  | done
12 | •I have already paid for the GRC Ecosystem Diagnostic and Performance Culture profile as can be seen from the invoice above. So, it should not ask me to pay for these 2 diagnostics again when I am buying a full report for another diagnostic. | 7 | done
13 | •View of Payment Form from GRC Implementation Validators Assessment. The checkbox should not be active for the diagnostics for which I have already paid |  | done
14 | •We had discussed this on call as follows | 8 | done
•Since we are giving the diagnostics free for individual account, the Amount column should be blank, but all the diagnostics should be listed along with the date.
•The amount should be visible in the Amount column when someone purchases the full report. Paid in bracket should also be visible, but “P” should be capital.
15 | •Also, when I am actually making the payment, it is getting recorded as a separate transaction instead of being recorded as buying the full report for the same diagnostic.
•See next slide for proposed view and guidelines to show the Transactions
16 | •This is what the table should look like when an individual account holder accesses Transactions after opening their Individual Account - default | 9 | done
It should list all the diagnostics, only 2 are shown here as an e.g.
•The data in the Full Report column should change as shown above once say the user buys the full report for any of the diagnostics. See example for Value Dynamics Diagnostic in the above table.
It should list all the diagnostics, only 2 are shown here as an e.g.
Entity Diagnostic: mentor-bi Admin
1 | •VDD (CC) - Only 1 person has responded to the survey but the report is generated. There have to be at least 5 responses for the report to be generated | 11 | done
•Also the report could be downloaded without clicking on the “Generate report” button. We have said that the Admin will click on Generate Report to generate the report, else the report will not get generated.
•The %age calculation in the report is still incorrect. E.g. in this case it should show1 out 5 (20%) responded to the survey.
2 | •Nothing happens when I click on “Generate Report” button and once I close the survey, the report gets generated automatically. | 12 | done
•The functionality that we have discussed is as follows:
•A report can be generated only when there are 5 responses (see previous slide where a report is getting generated with only 1 response
•A report can be generated only when the survey is closed
•Once the survey is closed, then the Mentor/CC Admin will click on the “Generate Report” button and the report will get generated. It will not get generated automatically on closing the survey .
3 | •There are 14 licenses available but it is now allowing a batch of 7 respondents to be created | 13 | done
•For mentor diagnostics, replace Core Creator consultant with mentor-bi team – this would be applicable for all mentor-bi diagnostics except VDD (CC)
4 | •While I was able to delete and replace a respondent, the new invitee (corecreatorsindia@gmail.com) did not get the survey invite email – which they should have to get their login credentials to complete the survey. | 14 | done
5 | •There are 7 invitees, but the report is taking only 6 – why is that? | 15 | done
6 | •Data has shifted to the right by 1 column – this is a problem for raw data in both Individual and Entity diagnostic for all diagnostics. | 16 | done
Entity Diagnostic: Client Admin
1 | •Pooja has created an Entity Account with 10 licenses and to it, I added another 10 licenses. | 18 | done
•However, on logging through the client portal and clicking on “Transactions”, the pop message says “Transaction Not Found”, which is incorrect.
The system should show both the transactions for PCP.
2 | •Continuing with the Client Admin portal, went from PCP (previous slide) to VDD. | 19 | done
•First on the left top corner, it shows the word “Enable” instead of “Value Dynamics Diagnostic”
Second, there is 1 license bought and used (this is Entity account view), yet on clicking “Transactions” the pop up says “Transactions Not Found” . This issue is across all the Diagnostic in the Entity account
3 | Replace “Remaining Amount” with “Amount Due” - it will be shorter | 20 | done
Entity Diagnostic: CC VDD
1 | There are 7 people who are invited to respond to the survey and 5 have responded to the survey. This data is captured incorrectly in the Survey Status for all surveys in VDD CC. This issue is encountered in some of the other diagnostics. It needs to be fixed across all diagnostics to ensure that the invited and responded data is captured correctly. Also does the data in the report come from this Survey Status page – because the percentage calculation in most reports in incorrect. | 22 | done
2 | •As highlighted on 2 Dec the page hangs – experienced that today also – on refreshing the page, can see that the username and passwords are generated. In the first round the page hung but no email went out to the survey invitees. In the 2nd round, the page hung but after refreshing it, the survey invite emails went to the invitees except for those with corecreator email id. | 23 | done
Also the field for “No of questions per page” is sometimes visible and sometimes not visible.
3 | •As highlighted on 2 Dec the page hangs – experienced that today also – on refreshing the page, nothing happens | 24 | done
In the first round of testing, no reminder mails went to the invitees. In the 2nd round of testing, the page hung but after refreshing, the reminder mail went to the survey invitees except to those with corecreators id.
4 | •Nothing happened after I clicked the “Attach Account” button, but when I refreshed the page and checked “Create Entity Account”, the account was already created. I didn’t get the email notifying me that the Entity Account has been created | 25 | done
This issue was raised on 2nd Dec but doesn’t seem to have been resolved.
5 | Replace “Company” with “Industry” in the above alert message in red. | 26 | done
6 | •The page layouts were also different in the first and second round of testing today – see how Active & Replace in seen in the first round of testing as compared to the 2nd round. What is seen in the 2nd round is the common view across all diagnostics. | 27 | Its depend on your device resolutions.
7 | •Pooja has responded to the CC VDD but when one logs into her account, CC VDD is not visible among the tiles under Survey Respondent (whether you log in through mentor website or CC test website link. | 28 | done
•Similarly, CC VDD is not visible in the Survey Respondent for any of the people who have submitted their responses
8 | There should be no “Employee” column in the Individual Diagnostic | 29 | done
It should start with “First Name”, “Last Name” and then whatever attributes have been defined in the survey pattern for the individual diagnostic
The scores in the raw data file is not getting captured correctly from the survey responses. It is not represented as per the set rating scale also. E.g. In the raw data, somewhere the score for Agree is shown as “10”, and in other places, it is “7” . Same for Disagree while as per the rating scale the score for only Strongly Agree is 10. E.g. The Raw data file given below is downloaded from the survey site, the actual response file is the analysis done based on the responses of the user
There are many data points in the excel sheet after the statements are over which should not be there.